## Settings
Settings of Golden trend-classic
Label | Value | Key (team.yaml)
name | Golden trend-classic | name
unit | PT | unit
features.products | FALSE | features.products
features.po | FALSE | features.po
features.production | FALSE | features.production
sprint.length_days | 14 | sprint.length_days
sprint.numbering | yearly | sprint.numbering
sprint.first.id | 2026.1 | sprint.first.id
sprint.first.start | 2026-01-07 | sprint.first.start
Reference capacity (PT) | 40 | forecast.reference_capacity
Window (sprints) | 5 | forecast.window
Plannable share | 0.8 | forecast.roadmap_share
Rounding (decimal places, rounded down) | 1 | forecast.rounding
Trend mode (fixed at export) | classic | forecast.trend_mode
forecast.horizon | 4 | forecast.horizon
capacity.overhead_share | 0 | capacity.overhead_share
capacity.rounding | 1 | capacity.rounding
Thin history n. velocity (fewer values than the window, at least 3) | FALSE
Thin history capacity | FALSE
Current status | 24.06.2026
Yellow cells are inputs (settings and sprint values); all other cells are formulas. The trend mode is fixed in the formulas.

## Forecast
Forecast Golden trend-classic
Inputs are yellow; the columns to the right calculate like the web interface (calculation).
Sprint | Start | End | Commitment (PT) | Velocity (PT) | Scope creep | Capacity (PD), recorded (input) | Capacity (PD), calculated from people and calendar | Source of the capacity | Capacity (PD), recorded or calculated | norm. velocity | Count n. velocity | Ø norm. velocity | norm. velocity trend | n. velocity known (avg or trend) | Count capacity | Avg capacity | Capacity trend | Capacity known (avg or trend) | Capacity for the Forecast PLAN (PD) | Forecast PLAN (PT) | Plannable (PT) | Small stuff (PT) | Fulfillment | Focus factor | Share of production access in the capacity | Capacity with production access (PD) | Capacity without production access (PD) | Forecast PLAN: up to with production access (PT) | Forecast PLAN: for all others (PT) | Σ planning per product (PT) | Forecast PLAN − Σ planning (PT)
2026.1 | 2026-01-07 | 2026-01-21 | 32 | 30 | 10% | 40 |  | recorded | 40 | 30 | 1 |  |  |  | 1 |  |  |  | 40 | 32 | 25.6 | 6.4 | 93.75% | 75%
2026.2 | 2026-01-21 | 2026-02-04 | 35 | 34 |  | 44 |  | recorded | 44 | 30.9091 | 2 |  |  |  | 2 |  |  |  | 44 | 35 | 28 | 7 | 97.14% | 77.27%
2026.3 | 2026-02-04 | 2026-02-18 | 33 | 28 | 5% | 38 |  | recorded | 38 | 29.4737 | 3 |  |  |  | 3 |  |  |  | 38 | 33 | 26.4 | 6.6 | 84.85% | 73.68%
2026.4 | 2026-02-18 | 2026-03-04 | 36 | 36 | 20% | 42 |  | recorded | 42 | 34.2857 | 4 |  |  |  | 4 |  |  |  | 42 | 36 | 28.8 | 7.2 | 100% | 85.71%
2026.5 | 2026-03-04 | 2026-03-18 | 30 |  | 0% | 40 |  | recorded | 40 |  | 4 |  |  |  | 5 | 40.8 |  | 40.8 | 40 | 30 | 24 | 6
2026.6 | 2026-03-18 | 2026-04-01 | 34 | 33 | 15% | 36 |  | recorded | 36 | 36.6667 | 5 | 32.267 |  | 32.267 | 6 | 40 |  | 40 | 36 | 34 | 27.2 | 6.8 | 97.06% | 91.67%
2026.7 | 2026-04-01 | 2026-04-15 | 38 | 38 |  | 44 |  | recorded | 44 | 34.5455 | 6 | 33.1761 |  | 33.1761 | 7 | 40 |  | 40 | 44 | 38 | 30.4 | 7.6 | 100% | 86.36%
2026.8 | 2026-04-15 | 2026-04-29 | 33 |  | 10% | 42 |  | recorded | 42 |  | 6 |  | 34.0852 | 34.0852 | 8 | 40.8 |  | 40.8 | 42 | 35.7 | 28.56 | 7.14
2026.9 | 2026-04-29 | 2026-05-13 | 32 | 31 | 5% | [5 empty] | 6 |  | 35.0455 | 35.0455 | 8 |  | 41.6 | 41.6 | 41.6 | 36.4 | 29.12 | 7.28 | 96.88%
2026.10 | 2026-05-13 | 2026-05-27 | 36 | 35 | 0% | 41 |  | recorded | 41 | 34.1463 | 7 | 33.8236 |  | 33.8236 | 9 | 40.6 |  | 40.6 | 41 | 36 | 28.8 | 7.2 | 97.22% | 85.37%
2026.11 | 2026-05-27 | 2026-06-10 | 37 | 37 | 10% | 40 |  | recorded | 40 | 37 | 8 | 35.3288 |  | 35.3288 | 10 | 40.6 |  | 40.6 | 40 | 37 | 29.6 | 7.4 | 100% | 92.5%
2026.12 | 2026-06-10 | 2026-06-24 | 36 |  |  | 39 |  | recorded | 39 |  | 8 |  | 36.8341 | 36.8341 | 11 | 41.2 |  | 41.2 | 39 | 35.9 | 28.72 | 7.18
2026.13 | 2026-06-24 | 2026-07-08 | [8 empty] | 8 |  | 38.4733 | 38.4733 | 11 |  | 41.8 | 41.8 | 41.8 | 40.2 | 32.16 | 8.04
2026.14 | 2026-07-08 | 2026-07-22 | [8 empty] | 8 |  | 40.1126 | 40.1126 | 11 |  | 42.4177 | 42.4177 | 42.4177 | 42.5 | 34 | 8.5
2026.15 | 2026-07-22 | 2026-08-05 | [8 empty] | 8 |  | 41.7518 | 41.7518 | 11 |  | 43.0355 | 43.0355 | 43.0355 | 44.9 | 35.92 | 8.98
2026.16 | 2026-08-05 | 2026-08-19 | [8 empty] | 8 |  | 43.3911 | 43.3911 | 11 |  | 43.6532 | 43.6532 | 43.6532 | 47.3 | 37.84 | 9.46
2026.17 | 2026-08-19 | 2026-09-02 | [8 empty] | 8 |  | 45.0303 | 45.0303 | 11 |  | 44.2709 | 44.2709 | 44.2709 | 49.8 | 39.84 | 9.96

## Sprint data
Sprint | State of the absences (unknown, expected, confirmed) | Forecast PLAN at planning, frozen (PT) | Carry-over (PT) | Backlog (PT) | Corrections of remaining effort (separated by spaces) | Of which not finished (PT) | Additionally done (PT) | Of which with production access, planning (PT) | Of which with production access, done (PT) | Note
2026.1 | unknown
2026.2 | unknown
2026.3 | unknown
2026.4 | unknown
2026.5 | unknown
2026.6 | unknown
2026.7 | unknown
2026.8 | unknown
2026.9 | unknown
2026.10 | unknown
2026.11 | unknown
2026.12 | unknown

## Absences
Sprint | Person (ID) | Name | days | Kind (absences = confirmed, expected_absences = announced)

## People
ID | Name | Country | Region | Work week | Production access | Member from | Member until | FTE

## Product list
ID | Name | PO | Handled from | Handled until | Fixed share (0–1)

## Product values
Sprint | Product (ID) | Product | PO | Standard (PT) | PO pre-planning (PT) | Planning (PT) | Done (PT) | of which production access (planning) (PT) | of which production access (done) (PT) | Planning without production access (PT) | Done without production access (PT)

## Prognoses
Sprint | Time | Comment | Commitment (PT) | Expected not finished (PT) | Additionally done (PT) | Expected done | Target sprint | Forecast PLAN | Pre-planning per product (ID=value; …)

## Trend
Sprint | norm. velocity | Ø norm. velocity | norm. velocity trend | Forecast PLAN | Velocity | Commitment
2026.1 | 30 | #N/A | #N/A | 32 | 30 | 32
2026.2 | 30.9091 | #N/A | #N/A | 35 | 34 | 35
2026.3 | 29.4737 | #N/A | #N/A | 33 | 28 | 33
2026.4 | 34.2857 | #N/A | #N/A | 36 | 36 | 36
2026.5 | #N/A | #N/A | #N/A | 30 | #N/A | 30
2026.6 | 36.6667 | 32.267 | #N/A | 34 | 33 | 34
2026.7 | 34.5455 | 33.1761 | #N/A | 38 | 38 | 38
2026.8 | #N/A | #N/A | 34.0852 | 35.7 | #N/A | 33
2026.9 | #N/A | #N/A | 35.0455 | 36.4 | 31 | 32
2026.10 | 34.1463 | 33.8236 | #N/A | 36 | 35 | 36
2026.11 | 37 | 35.3288 | #N/A | 37 | 37 | 37
2026.12 | #N/A | #N/A | 36.8341 | 35.9 | #N/A | 36
2026.13 | #N/A | #N/A | 38.4733 | 40.2 | #N/A | #N/A
2026.14 | #N/A | #N/A | 40.1126 | 42.5 | #N/A | #N/A
2026.15 | #N/A | #N/A | 41.7518 | 44.9 | #N/A | #N/A
2026.16 | #N/A | #N/A | 43.3911 | 47.3 | #N/A | #N/A
2026.17 | #N/A | #N/A | 45.0303 | 49.8 | #N/A | #N/A