## Settings
Settings of Demo-Team
Label | Value | Key (team.yaml)
name | Demo-Team | name
unit | PT | unit
features.products | TRUE | features.products
features.po | TRUE | features.po
features.production | TRUE | features.production
sprint.length_days | 14 | sprint.length_days
sprint.numbering | yearly | sprint.numbering
sprint.first.id | 2026.1 | sprint.first.id
sprint.first.start | 2026-01-07 | sprint.first.start
Reference capacity (PT) | 45 | forecast.reference_capacity
Window (sprints) | 5 | forecast.window
Plannable share | 0.8 | forecast.roadmap_share
Rounding (decimal places, rounded down) | 1 | forecast.rounding
Trend mode (fixed at export) | flat | forecast.trend_mode
forecast.horizon | 3 | forecast.horizon
capacity.overhead_share | 0 | capacity.overhead_share
capacity.region | NW | capacity.region
capacity.rounding | 1 | capacity.rounding
Thin history n. velocity (fewer values than the window, at least 3)
Thin history capacity
Current status | 15.10.2026
Yellow cells are inputs (settings and sprint values); all other cells are formulas. The trend mode is fixed in the formulas.

## Forecast
Forecast Demo-Team
Inputs are yellow; the columns to the right calculate like the web interface (calculation).
Sprint | Start | End | Commitment (PT) | Velocity (PT) | Scope creep | Capacity (PD), recorded (input) | Capacity (PD), calculated from people and calendar | Source of the capacity | Capacity (PD), recorded or calculated | norm. velocity | Count n. velocity | Ø norm. velocity | norm. velocity trend | n. velocity known (avg or trend) | Count capacity | Avg capacity | Capacity trend | Capacity known (avg or trend) | Capacity for the Forecast PLAN (PD) | Forecast PLAN (PT) | Plannable (PT) | Small stuff (PT) | Fulfillment | Focus factor | Share of production access in the capacity | Capacity with production access (PD) | Capacity without production access (PD) | Forecast PLAN: up to with production access (PT) | Forecast PLAN: for all others (PT) | Σ planning per product (PT) | Forecast PLAN − Σ planning (PT)
2026.1 | 2026-01-07 | 2026-01-21 | 11 | 10.5 | 0% | 33 |  | recorded
2026.2 | 2026-01-21 | 2026-02-04 | 11.25 | 12.75 | 20% | 32 |  | recorded
2026.3 | 2026-02-04 | 2026-02-18 | 11.5 | 9.25 | 5% | 34.6 |  | recorded
2026.4 | 2026-02-18 | 2026-03-04 | 14.25 | 14.5 | 10% | 37.5 |  | recorded
2026.5 | 2026-03-04 | 2026-03-18 | 11.75 | 10.25 | 10% | 33.2 |  | recorded
2026.6 | 2026-03-18 | 2026-04-01 | 15 | 13.75 | 0% | 40 |  | recorded
2026.7 | 2026-04-01 | 2026-04-15 | 7.75 | 6 | 5% | 23.4 |  | recorded
2026.8 | 2026-04-15 | 2026-04-29 | 15.25 | 12.75 | 5% | 37 |  | recorded
2026.9 | 2026-04-29 | 2026-05-13 | 11 | 11.75 | 20% | 32.7 |  | recorded
2026.10 | 2026-05-13 | 2026-05-27 | 10 | 9.5 | 20% | 29 |  | recorded
2026.11 | 2026-05-27 | 2026-06-10 | 14.25 | 14.5 | 20% | 38.5 |  | recorded
2026.12 | 2026-06-10 | 2026-06-24 | 11.75 | 13.5 | 10% | 32.1 |  | recorded
2026.13 | 2026-06-24 | 2026-07-08 | 13.5 | 10.25 | 0% | 41 |  | recorded
2026.14 | 2026-07-08 | 2026-07-22 | 13.25 | 12.5 | 5% | 35.4 |  | recorded
2026.15 | 2026-07-22 | 2026-08-05 | 14.5 | 16.5 | 5% | 38.6 |  | recorded
2026.16 | 2026-08-05 | 2026-08-19 | 13.25 | 14 | 20% | 34 |  | recorded
2026.17 | 2026-08-19 | 2026-09-02 | 12.75 | 11.5 | 0% | 31.7 |  | recorded
2026.18 | 2026-09-02 | 2026-09-16 | 10 | 10.5 | 5% | 28.5 |  | recorded
2026.19 | 2026-09-16 | 2026-09-30 | 11.5 | 12.75 | 0% | 32.5 |  | recorded
2026.20 | 2026-09-30 | 2026-10-14 | 12 | 9.75 | 5% | 29 |  | recorded
2026.21 | 2026-10-14 | 2026-10-28 | 10 |  |  |  | 25.5 | people list
2026.22 | 2026-10-28 | 2026-11-11 |  |  |  |  | 30 | people list
2026.23 | 2026-11-11 | 2026-11-25 |  |  |  |  | 30.4375 | expected absences
2026.24 | 2026-11-25 | 2026-12-09 |  |  |  |  | 30.4375 | expected absences

## Sprint data
Sprint | State of the absences (unknown, expected, confirmed) | Forecast PLAN at planning, frozen (PT) | Carry-over (PT) | Backlog (PT) | Corrections of remaining effort (separated by spaces) | Of which not finished (PT) | Additionally done (PT) | Of which with production access, planning (PT) | Of which with production access, done (PT) | Note
2026.1 |  |  | 1.5 | 9.5 | 0
2026.2 |  |  | 1.75 | 9.5 | 0.75
2026.3 |  |  | 2.5 | 9 | 0.25
2026.4 |  |  | 0.25 | 14 | 0.25
2026.5 |  |  | 0.5 | 11.25 | 0
2026.6 |  |  | 0.5 | 14.5 | 1.5
2026.7 |  |  | 0.25 | 7.5 | 1
2026.8 |  |  | 1 | 14.25 | 0.75
2026.9 |  |  | 1.25 | 9.75 | 1.25
2026.10 |  |  | 0.5 | 9.5 | 0.25
2026.11 |  |  | 1 | 13.25 | 1.5
2026.12 |  |  | 1.5 | 10.25 | 0.25
2026.13 |  |  | 0.5 | 13 | 0.5
2026.14 |  |  | 0.25 | 13 | 1.5
2026.15 |  |  | 2 | 12.5 | 0.25
2026.16 |  |  | 0.75 | 12.5 | 0.25
2026.17 |  |  | 2.25 | 10.5 | 0.75
2026.18 |  |  | 1.75 | 8.25 | 1.25
2026.19 |  |  | 0.5 | 11 | 1
2026.20 |  |  | 2.25 | 9.75 | 0.75
2026.21 |  |  | 0.25 | 9.75 | 1.5
2026.22

## Absences
Sprint | Person (ID) | Name | days | Kind (absences = confirmed, expected_absences = announced)
2026.1 | anna | Anna | 2 | absences
2026.1 | cem | Cem | 3 | absences
2026.2 | ben | Ben | 3 | absences
2026.2 | cem | Cem | 3 | absences
2026.3 | ben | Ben | 3 | absences
2026.3 | emil | Emil | 0.5 | absences
2026.4 | cem | Cem | 0.5 | absences
2026.4 | dana | Dana | 2 | absences
2026.5 | anna | Anna | 2 | absences
2026.5 | ben | Ben | 5 | absences
2026.5 | cem | Cem | 5 | absences
2026.5 | dana | Dana | 2 | absences
2026.5 | emil | Emil | 1 | absences
2026.6 | anna | Anna | 2 | absences
2026.6 | ben | Ben | 5 | absences
2026.6 | cem | Cem | 1 | absences
2026.7 | anna | Anna | 2 | absences
2026.7 | ben | Ben | 2 | absences
2026.7 | cem | Cem | 2 | absences
2026.7 | dana | Dana | 5 | absences
2026.7 | emil | Emil | 5 | absences
2026.8 | anna | Anna | 5 | absences
2026.8 | ben | Ben | 1 | absences
2026.8 | cem | Cem | 3 | absences
2026.8 | dana | Dana | 2 | absences
2026.9 | ben | Ben | 0.5 | absences
2026.9 | cem | Cem | 3 | absences
2026.9 | dana | Dana | 3 | absences
2026.9 | emil | Emil | 5 | absences
2026.10 | anna | Anna | 1 | absences
2026.10 | ben | Ben | 3 | absences
2026.10 | cem | Cem | 2 | absences
2026.10 | dana | Dana | 3 | absences
2026.10 | emil | Emil | 0.5 | absences
2026.11 | ben | Ben | 1 | absences
2026.11 | cem | Cem | 1 | absences
2026.12 | ben | Ben | 5 | absences
2026.12 | cem | Cem | 3 | absences
2026.12 | dana | Dana | 3 | absences
2026.12 | emil | Emil | 3 | absences
2026.13 | cem | Cem | 2 | absences
2026.14 | anna | Anna | 3 | absences
2026.14 | cem | Cem | 1 | absences
2026.14 | dana | Dana | 2 | absences
2026.14 | emil | Emil | 2 | absences
2026.15 | dana | Dana | 2 | absences
2026.15 | emil | Emil | 1 | absences
2026.16 | cem | Cem | 1 | absences
2026.17 | anna | Anna | 2 | absences
2026.17 | ben | Ben | 0.5 | absences
2026.17 | cem | Cem | 0.5 | absences
2026.17 | dana | Dana | 0.5 | absences
2026.18 | ben | Ben | 1 | absences
2026.18 | cem | Cem | 5 | absences
2026.18 | dana | Dana | 1 | absences
2026.19 | anna | Anna | 2 | absences
2026.19 | cem | Cem | 0.5 | absences
2026.20 | anna | Anna | 5 | absences
2026.20 | ben | Ben | 2 | absences
2026.21 | ben | Ben | 3 | absences
2026.21 | cem | Cem | 5 | absences
2026.21 | dana | Dana | 3 | absences
2026.22 | cem | Cem | 5 | absences

## People
ID | Name | Country | Region | Work week | Production access | Member from | Member until | FTE
anna | Anna |  |  |  |  | 2025-01-01 |  | 1
ben | Ben |  |  |  |  | 2025-01-01 | 2026-05-31 | 1
ben | Ben |  |  |  |  | 2026-06-01 |  | 0.5
cem | Cem |  | BY |  |  | 2025-01-01 |  | 1
dana | Dana |  |  |  |  | 2026-03-01 |  | 1
emil | Emil |  |  |  |  | 2025-01-01 | 2026-07-31 | 0.8

## Product list
ID | Name | PO | Handled from | Handled until | Fixed share (0–1)
webshop |  | Alex
app | Mobile App | Alex
portal | Kundenportal | Bea | 2026-09-02
altsystem | Altsystem | Bea |  | 2026-09-15

## Product values
Sprint | Product (ID) | Product | PO | Standard (PT) | PO pre-planning (PT) | Planning (PT) | Done (PT) | of which production access (planning) (PT) | of which production access (done) (PT) | Planning without production access (PT) | Done without production access (PT)
2026.1 | webshop | Webshop | Alex | 3.6667
2026.1 | app | Mobile App | Alex | 3.6667
2026.1 | altsystem | Altsystem | Bea | 3.6667
2026.2 | webshop | Webshop | Alex | 3.7333
2026.2 | app | Mobile App | Alex | 3.7333
2026.2 | altsystem | Altsystem | Bea | 3.7333
2026.3 | webshop | Webshop | Alex | 3.8333
2026.3 | app | Mobile App | Alex | 3.8333
2026.3 | altsystem | Altsystem | Bea | 3.8333
2026.4 | webshop | Webshop | Alex | 4.7333
2026.4 | app | Mobile App | Alex | 4.7333
2026.4 | altsystem | Altsystem | Bea | 4.7333
2026.5 | webshop | Webshop | Alex | 3.9
2026.5 | app | Mobile App | Alex | 3.9
2026.5 | altsystem | Altsystem | Bea | 3.9
2026.6 | webshop | Webshop | Alex | 5
2026.6 | app | Mobile App | Alex | 5
2026.6 | altsystem | Altsystem | Bea | 5
2026.7 | webshop | Webshop | Alex | 2.5667
2026.7 | app | Mobile App | Alex | 2.5667
2026.7 | altsystem | Altsystem | Bea | 2.5667
2026.8 | webshop | Webshop | Alex | 5.0667
2026.8 | app | Mobile App | Alex | 5.0667
2026.8 | altsystem | Altsystem | Bea | 5.0667
2026.9 | webshop | Webshop | Alex | 3.6667
2026.9 | app | Mobile App | Alex | 3.6667
2026.9 | altsystem | Altsystem | Bea | 3.6667
2026.10 | webshop | Webshop | Alex | 3.3333
2026.10 | app | Mobile App | Alex | 3.3333
2026.10 | altsystem | Altsystem | Bea | 3.3333
2026.11 | webshop | Webshop | Alex | 4.7333
2026.11 | app | Mobile App | Alex | 4.7333
2026.11 | altsystem | Altsystem | Bea | 4.7333
2026.12 | webshop | Webshop | Alex | 3.9
2026.12 | app | Mobile App | Alex | 3.9
2026.12 | altsystem | Altsystem | Bea | 3.9
2026.13 | webshop | Webshop | Alex | 4.5
2026.13 | app | Mobile App | Alex | 4.5
2026.13 | altsystem | Altsystem | Bea | 4.5
2026.14 | webshop | Webshop | Alex | 4.4
2026.14 | app | Mobile App | Alex | 4.4
2026.14 | altsystem | Altsystem | Bea | 4.4
2026.15 | webshop | Webshop | Alex | 4.8333
2026.15 | app | Mobile App | Alex | 4.8333
2026.15 | altsystem | Altsystem | Bea | 4.8333
2026.16 | webshop | Webshop | Alex | 4.4
2026.16 | app | Mobile App | Alex | 4.4
2026.16 | altsystem | Altsystem | Bea | 4.4
2026.17 | webshop | Webshop | Alex | 4.2333 | 5 | 5 | 4.5
2026.17 | app | Mobile App | Alex | 4.2333 | 4 | 4.75 | 4.5
2026.17 | altsystem | Altsystem | Bea | 4.2333 | 3 | 3 | 2.5
2026.18 | webshop | Webshop | Alex | 2.5 | 3 | 3 | 3.5
2026.18 | app | Mobile App | Alex | 2.5 | 3 | 2.5 | 3
2026.18 | portal | Kundenportal | Bea | 2.5 | 2 | 2.5 | 2
2026.18 | altsystem | Altsystem | Bea | 2.5 | 2 | 2 | 2
2026.19 | webshop | Webshop | Alex | 3.8333 | 4 | 4 | 4.5
2026.19 | app | Mobile App | Alex | 3.8333 | 4 | 4 | 4.25
2026.19 | portal | Kundenportal | Bea | 3.8333 | 4 | 3.5 | 4
2026.20 | webshop | Webshop | Alex | 4 | 4 | 4.5 | 4
2026.20 | app | Mobile App | Alex | 4 | 4 | 4 | 3
2026.20 | portal | Kundenportal | Bea | 4 | 4 | 3.5 | 2.75
2026.21 | webshop | Webshop | Alex | 3.1667 | 3.5 | 4
2026.21 | app | Mobile App | Alex | 3.1667 | 3 | 3
2026.21 | portal | Kundenportal | Bea | 3.1667 | 3 | 3
2026.22 | webshop | Webshop | Alex | 3.7333 | 3
2026.22 | app | Mobile App | Alex | 3.7333 | 3
2026.22 | portal | Kundenportal | Bea | 3.7333 | 4
2026.23 | webshop | Webshop | Alex | 3.7667
2026.23 | app | Mobile App | Alex | 3.7667
2026.23 | portal | Kundenportal | Bea | 3.7667
2026.24 | webshop | Webshop | Alex | 3.7667
2026.24 | app | Mobile App | Alex | 3.7667
2026.24 | portal | Kundenportal | Bea | 3.7667

## Prognoses
Sprint | Time | Comment | Commitment (PT) | Expected not finished (PT) | Additionally done (PT) | Expected done | Target sprint | Forecast PLAN | Pre-planning per product (ID=value; …)

## Trend
Sprint | norm. velocity | Ø norm. velocity | norm. velocity trend | Forecast PLAN | Velocity | Commitment