## Settings
Settings of Golden tickets-products
Label | Value | Key (team.yaml)
name | Golden tickets-products | name
unit | PT | unit
features.products | TRUE | features.products
features.po | TRUE | features.po
features.production | TRUE | features.production
features.tickets | TRUE | features.tickets
sprint.length_days | 14 | sprint.length_days
sprint.numbering | yearly | sprint.numbering
sprint.first.id | 2026.1 | sprint.first.id
sprint.first.start | 2026-05-06 | sprint.first.start
Reference capacity (PT) | 40 | forecast.reference_capacity
Window (sprints) | 5 | forecast.window
Plannable share | 0.8 | forecast.roadmap_share
Rounding (decimal places, rounded down) | 1 | forecast.rounding
Trend mode (fixed at export) | flat | forecast.trend_mode
forecast.horizon | 3 | forecast.horizon
capacity.overhead_share | 0 | capacity.overhead_share
capacity.rounding | 1 | capacity.rounding
Thin history n. velocity (fewer values than the window, at least 3) | FALSE
Thin history capacity | FALSE
Current status | 08.07.2026
Yellow cells are inputs (settings and sprint values); all other cells are formulas. The trend mode is fixed in the formulas.

## Forecast
Forecast Golden tickets-products
Inputs are yellow; the columns to the right calculate like the web interface (calculation).
Sprint | Start | End | Commitment (PT) | Velocity (PT) | Scope creep | Capacity (PD), recorded (input) | Capacity (PD), calculated from people and calendar | Source of the capacity | Capacity (PD), recorded or calculated | norm. velocity | Count n. velocity | Ø norm. velocity | norm. velocity trend | n. velocity known (avg or trend) | Count capacity | Avg capacity | Capacity trend | Capacity known (avg or trend) | Capacity for the Forecast PLAN (PD) | Forecast PLAN (PT) | Plannable (PT) | Small stuff (PT) | Fulfillment | Focus factor | Share of production access in the capacity | Capacity with production access (PD) | Capacity without production access (PD) | Forecast PLAN: up to with production access (PT) | Forecast PLAN: for all others (PT) | Σ planning per product (PT) | Forecast PLAN − Σ planning (PT)
2026.1 | 2026-05-06 | 2026-05-20 | 32 | 31 |  | 40 |  | recorded | 40 | 31 | 1 |  |  |  | 1 |  |  |  | 40 | 32 | 25.6 | 6.4 | 96.88% | 77.5%
2026.2 | 2026-05-20 | 2026-06-03 | 30 | 29 |  | 38 |  | recorded | 38 | 30.5263 | 2 |  |  |  | 2 |  |  |  | 38 | 30 | 24 | 6 | 96.67% | 76.32%
2026.3 | 2026-06-03 | 2026-06-17 | 34 | 35 |  | 40 |  | recorded | 40 | 35 | 3 |  |  |  | 3 |  |  |  | 40 | 34 | 27.2 | 6.8 | 102.9% | 87.5%
2026.4 | 2026-06-17 | 2026-07-01 | 34 | 33 |  | 42 |  | recorded | 42 | 31.4286 | 4 |  |  |  | 4 |  |  |  | 42 | 34 | 27.2 | 6.8 | 97.06% | 78.57%
2026.5 | 2026-07-01 | 2026-07-15 | 31 | 30 |  | 40 |  | recorded | 40 | 30 | 5 | 31.591 |  | 31.591 | 5 | 40 |  | 40 | 40 | 31 | 24.8 | 6.2 | 96.77% | 75%
2026.6 | 2026-07-15 | 2026-07-29 | 32 |  |  | 40 |  | recorded | 40 |  | 5 |  | 31.591 | 31.591 | 6 | 40 |  | 40 | 40 | 31.5 | 25.2 | 6.3
2026.7 | 2026-07-29 | 2026-08-12 | [8 empty] | 5 |  | 31.591 | 31.591 | 6 |  | 40 | 40 | 40 | 31.5 | 25.2 | 6.3
2026.8 | 2026-08-12 | 2026-08-26 | [8 empty] | 5 |  | 31.591 | 31.591 | 6 |  | 40 | 40 | 40 | 31.5 | 25.2 | 6.3

## Sprint data
Sprint | State of the absences (unknown, expected, confirmed) | Forecast PLAN at planning, frozen (PT) | Carry-over (PT) | Backlog (PT) | Corrections of remaining effort (separated by spaces) | Of which not finished (PT) | Additionally done (PT) | Of which with production access, planning (PT) | Of which with production access, done (PT) | Note
2026.1 | unknown
2026.2 | unknown
2026.3 | unknown
2026.4 | unknown
2026.5 | unknown
2026.6 | unknown
2026.7

## Absences
Sprint | Person (ID) | Name | days | Kind (absences = confirmed, expected_absences = announced)

## People
ID | Name | Country | Region | Work week | Production access | Member from | Member until | FTE

## Product list
ID | Name | PO | Handled from | Handled until | Fixed share (0–1)
web | Web | Alex |  |  | 0.5
app | App | Alex
old | Old | Bea |  | 2026-08-20
new | New | Bea | 2026-08-05

## Product values
Sprint | Product (ID) | Product | PO | Standard (PT) | PO pre-planning (PT) | Planning (PT) | Done (PT) | of which production access (planning) (PT) | of which production access (done) (PT) | Planning without production access (PT) | Done without production access (PT)
2026.1 | web | Web | Alex | 16
2026.1 | app | App | Alex | 8
2026.1 | old | Old | Bea | 8
2026.2 | web | Web | Alex | 15
2026.2 | app | App | Alex | 7.5
2026.2 | old | Old | Bea | 7.5
2026.3 | web | Web | Alex | 17
2026.3 | app | App | Alex | 8.5
2026.3 | old | Old | Bea | 8.5
2026.4 | web | Web | Alex | 17
2026.4 | app | App | Alex | 8.5
2026.4 | old | Old | Bea | 8.5
2026.5 | web | Web | Alex | 15.5
2026.5 | app | App | Alex | 7.75
2026.5 | old | Old | Bea | 7.75
2026.6 | web | Web | Alex | 15.75
2026.6 | app | App | Alex | 7.875
2026.6 | old | Old | Bea | 7.875
2026.7 | web | Web | Alex | 15.75
2026.7 | app | App | Alex | 5.25
2026.7 | old | Old | Bea | 5.25
2026.7 | new | New | Bea | 5.25
2026.8 | web | Web | Alex | 15.75
2026.8 | app | App | Alex | 5.25
2026.8 | old | Old | Bea | 5.25
2026.8 | new | New | Bea | 5.25

## Prognoses
Sprint | Time | Comment | Commitment (PT) | Expected not finished (PT) | Additionally done (PT) | Expected done | Target sprint | Forecast PLAN | Pre-planning per product (ID=value; …)

## Trend
Sprint | norm. velocity | Ø norm. velocity | norm. velocity trend | Forecast PLAN | Velocity | Commitment
2026.1 | 31 | #N/A | #N/A | 32 | 31 | 32
2026.2 | 30.5263 | #N/A | #N/A | 30 | 29 | 30
2026.3 | 35 | #N/A | #N/A | 34 | 35 | 34
2026.4 | 31.4286 | #N/A | #N/A | 34 | 33 | 34
2026.5 | 30 | 31.591 | #N/A | 31 | 30 | 31
2026.6 | #N/A | #N/A | 31.591 | 31.5 | #N/A | 32
2026.7 | #N/A | #N/A | 31.591 | 31.5 | #N/A | #N/A
2026.8 | #N/A | #N/A | 31.591 | 31.5 | #N/A | #N/A