## Settings
Settings of Golden products-edge
Label | Value | Key (team.yaml)
name | Golden products-edge | name
unit | PT | unit
features.products | TRUE | features.products
features.po | TRUE | features.po
features.production | TRUE | features.production
sprint.length_days | 14 | sprint.length_days
sprint.numbering | yearly | sprint.numbering
sprint.first.id | 2026.1 | sprint.first.id
sprint.first.start | 2026-01-07 | sprint.first.start
Reference capacity (PT) | 40 | forecast.reference_capacity
Window (sprints) | 5 | forecast.window
Plannable share | 0.75 | forecast.roadmap_share
Rounding (decimal places, rounded down) | 1 | forecast.rounding
Trend mode (fixed at export) | flat | forecast.trend_mode
forecast.horizon | 3 | forecast.horizon
forecast.product_basis | roadmap | forecast.product_basis
capacity.overhead_share | 0 | capacity.overhead_share
capacity.rounding | 1 | capacity.rounding
Thin history n. velocity (fewer values than the window, at least 3) | FALSE
Thin history capacity | FALSE
Current status | 24.06.2026
Yellow cells are inputs (settings and sprint values); all other cells are formulas. The trend mode is fixed in the formulas.

## Forecast
Forecast Golden products-edge
Inputs are yellow; the columns to the right calculate like the web interface (calculation).
Sprint | Start | End | Commitment (PT) | Velocity (PT) | Scope creep | Capacity (PD), recorded (input) | Capacity (PD), calculated from people and calendar | Source of the capacity | Capacity (PD), recorded or calculated | norm. velocity | Count n. velocity | Ø norm. velocity | norm. velocity trend | n. velocity known (avg or trend) | Count capacity | Avg capacity | Capacity trend | Capacity known (avg or trend) | Capacity for the Forecast PLAN (PD) | Forecast PLAN (PT) | Plannable (PT) | Small stuff (PT) | Fulfillment | Focus factor | Share of production access in the capacity | Capacity with production access (PD) | Capacity without production access (PD) | Forecast PLAN: up to with production access (PT) | Forecast PLAN: for all others (PT) | Σ planning per product (PT) | Forecast PLAN − Σ planning (PT)
2026.1 | 2026-01-07 | 2026-01-21 | 32 | 30 |  | 40 |  | recorded | 40 | 30 | 1 |  |  |  | 1 |  |  |  | 40 | 32 | 24 | 8 | 93.75% | 75% | 11.76% | 4.7059 | 35.2941 | 3.7647 | 28.2353 | 26.5 | 5.5
2026.2 | 2026-01-21 | 2026-02-04 | 35 | 34 |  | 44 |  | recorded | 44 | 30.9091 | 2 |  |  |  | 2 |  |  |  | 44 | 35 | 26.25 | 8.75 | 97.14% | 77.27% | 11.63% | 5.1163 | 38.8837 | 4.0698 | 30.9302 | 27 | 8
2026.3 | 2026-02-04 | 2026-02-18 | 33 | 28 |  | 38 |  | recorded | 38 | 29.4737 | 3 |  |  |  | 3 |  |  |  | 38 | 33 | 24.75 | 8.25 | 84.85% | 73.68% | 11.99% | 4.5564 | 33.4436 | 3.9568 | 29.0432 | 18 | 15
2026.4 | 2026-02-18 | 2026-03-04 | 36 | 36 |  | 42 |  | recorded | 42 | 34.2857 | 4 |  |  |  | 4 |  |  |  | 42 | 36 | 27 | 9 | 100% | 85.71% | 12.22% | 5.1345 | 36.8655 | 4.401 | 31.599
2026.5 | 2026-03-04 | 2026-03-18 | 34 | 33 |  | 40 |  | recorded | 40 | 33 | 5 | 31.5337 |  | 31.5337 | 5 | 40.8 |  | 40.8 | 40 | 34 | 25.5 | 8.5 | 97.06% | 82.5% | 11.63% | 4.6512 | 35.3488 | 3.9535 | 30.0465
2026.6 | 2026-03-18 | 2026-04-01 | 32 | 31 |  | 41 |  | recorded | 41 | 30.2439 | 6 | 31.5825 |  | 31.5825 | 6 | 41 |  | 41 | 41 | 32 | 24 | 8 | 96.88% | 75.61% | 4.054% | 1.6622 | 39.3378 | 1.2973 | 30.7027
2026.7 | 2026-04-01 | 2026-04-15 |  |  |  |  | 67.2 | Calendar, absences unknown | 67.2 |  | 6 |  | 31.5825 | 31.5825 | 7 | 45.64 |  | 45.64 | 67.2 | 53 | 39.75 | 13.25
2026.8 | 2026-04-15 | 2026-04-29 |  |  |  |  | 76 | Calendar, absences unknown | 76 |  | 6 |  | 31.5825 | 31.5825 | 8 | 53.24 |  | 53.24 | 76 | 60 | 45 | 15
2026.9 | 2026-04-29 | 2026-05-13 |  |  |  |  | 70.6 | Calendar, absences unknown | 70.6 |  | 6 |  | 31.5825 | 31.5825 | 9 | 58.96 |  | 58.96 | 70.6 | 55.7 | 41.775 | 13.925
2026.10 | 2026-05-13 | 2026-05-27 |  |  |  |  | 64 | Calendar, absences unknown | 64 |  | 6 |  | 31.5825 | 31.5825 | 10 | 63.76 |  | 63.76 | 64 | 50.5 | 37.875 | 12.625
2026.11 | 2026-05-27 | 2026-06-10 |  |  |  |  | 72 | Calendar, absences unknown | 72 |  | 6 |  | 31.5825 | 31.5825 | 11 | 69.96 |  | 69.96 | 72 | 56.8 | 42.6 | 14.2
2026.12 | 2026-06-10 | 2026-06-24 |  |  |  |  | 74.2 | Calendar, absences unknown | 74.2 |  | 6 |  | 31.5825 | 31.5825 | 12 | 71.36 |  | 71.36 | 74.2 | 58.5 | 43.875 | 14.625
2026.13 | 2026-06-24 | 2026-07-08 |  |  |  |  | 75 | Calendar, absences unknown | 75 |  | 6 |  | 31.5825 | 31.5825 | 13 | 71.16 |  | 71.16 | 75 | 59.2 | 44.4 | 14.8
2026.14 | 2026-07-08 | 2026-07-22 |  |  |  |  | 76 | Calendar, absences unknown | 76 |  | 6 |  | 31.5825 | 31.5825 | 14 | 72.24 |  | 72.24 | 76 | 60 | 45 | 15
2026.15 | 2026-07-22 | 2026-08-05 |  |  |  |  | 76 | Calendar, absences unknown | 76 |  | 6 |  | 31.5825 | 31.5825 | 15 | 74.64 |  | 74.64 | 76 | 60 | 45 | 15
2026.16 | 2026-08-05 | 2026-08-19 |  |  |  |  | 76 | Calendar, absences unknown | 76 |  | 6 |  | 31.5825 | 31.5825 | 16 | 75.44 |  | 75.44 | 76 | 60 | 45 | 15

## Sprint data
Sprint | State of the absences (unknown, expected, confirmed) | Forecast PLAN at planning, frozen (PT) | Carry-over (PT) | Backlog (PT) | Corrections of remaining effort (separated by spaces) | Of which not finished (PT) | Additionally done (PT) | Of which with production access, planning (PT) | Of which with production access, done (PT) | Note
2026.1 | unknown | 25.5
2026.2 | unknown | 27
2026.3 | unknown
2026.4 | unknown | 30
2026.5 | unknown | [6 empty] | 3 | 2.5
2026.6 | unknown
2026.7
2026.8
2026.9

## Absences
Sprint | Person (ID) | Name | days | Kind (absences = confirmed, expected_absences = announced)

## People
ID | Name | Country | Region | Work week | Production access | Member from | Member until | FTE
anna | Anna |  |  |  |  | 2025-01-01 |  | 1
ben | Ben |  |  |  |  | 2025-01-01 | 2026-08-31 | 1
ben | Ben |  |  |  |  | 2026-09-01 |  | 0.5
cem | Cem |  | BY |  |  | 2025-01-01 |  | 1
dana | Dana | US | CA |  |  | 2025-06-01 |  | 1
eli | Eli | CN |  |  |  | 2025-06-01 |  | 0.8
fadi | Fadi | SA |  |  |  | 2026-01-01 |  | 1
gina | Gina |  |  | mon,tue,wed,thu |  | 2025-01-01 |  | 1
hugo | Hugo |  |  | sun-thu |  | 2025-01-01 |  | 1
ines | Ines |  |  |  | TRUE | 2025-01-01 | 2026-03-20 | 1
jonas | Jonas |  |  |  | TRUE | 2026-09-15 |  | 1

## Product list
ID | Name | PO | Handled from | Handled until | Fixed share (0–1)
web | Web | Alex |  |  | 0.4
app | App | Alex |  |  | 0.35
api | API | Bea
old | Old | Bea |  | 2026-03-01
new | New |  | 2026-03-04

## Product values
Sprint | Product (ID) | Product | PO | Standard (PT) | PO pre-planning (PT) | Planning (PT) | Done (PT) | of which production access (planning) (PT) | of which production access (done) (PT) | Planning without production access (PT) | Done without production access (PT)
2026.1 | web | Web | Alex | 7.65 | 10 | 11 | 10.5 | 2 | 1.5 | 9 | 9
2026.1 | app | App | Alex | 6.6937 | 9 | 9 | 9
2026.1 | api | API | Bea | 2.3906 | 6 | 5.5 | 5
2026.1 | old | Old | Bea | 2.3906 |  |  | 1
2026.1 | aa | aa |  |  |  | 1
2026.1 | zz | zz |  |  |  |  | 0.5
2026.2 | web | Web | Alex | 8.1 |  | 12 | 12.5
2026.2 | app | App | Alex | 7.0875 |  | 9
2026.2 | api | API | Bea | 2.5312 |  | 6 | 6.5 | 1 |  | 5
2026.2 | old | Old | Bea | 2.5312 |  |  | 0
2026.3 | web | Web | Alex | 9.9 |  | 11 | 10 | 30 |  | -19
2026.3 | app | App | Alex | 8.6625
2026.3 | api | API | Bea | 3.0938 |  | 7 | 7
2026.3 | old | Old | Bea | 3.0938
2026.3 | new | New |  |  |  |  | 2 |  | 1 |  | 1
2026.4 | web | Web | Alex | 9
2026.4 | app | App | Alex | 7.875 |  |  | 8
2026.4 | api | API | Bea | 2.8125
2026.4 | old | Old | Bea | 2.8125
2026.4 | new | New |  |  |  |  | 3
2026.5 | web | Web | Alex | 10.2
2026.5 | app | App | Alex | 8.925
2026.5 | api | API | Bea | 3.1875
2026.5 | new | New |  | 3.1875
2026.6 | web | Web | Alex | 9.6 | 9
2026.6 | app | App | Alex | 8.4 | 8
2026.6 | api | API | Bea | 3
2026.6 | new | New |  | 3
2026.7 | web | Web | Alex | 15.9
2026.7 | app | App | Alex | 13.9125
2026.7 | api | API | Bea | 4.9688
2026.7 | new | New |  | 4.9688
2026.8 | web | Web | Alex | 18
2026.8 | app | App | Alex | 15.75
2026.8 | api | API | Bea | 5.625
2026.8 | new | New |  | 5.625
2026.9 | web | Web | Alex | 16.71
2026.9 | app | App | Alex | 14.6212
2026.9 | api | API | Bea | 5.2219
2026.9 | new | New |  | 5.2219
2026.10 | web | Web | Alex | 15.15
2026.10 | app | App | Alex | 13.2562
2026.10 | api | API | Bea | 4.7344
2026.10 | new | New |  | 4.7344
2026.11 | web | Web | Alex | 17.04
2026.11 | app | App | Alex | 14.91
2026.11 | api | API | Bea | 5.325
2026.11 | new | New |  | 5.325
2026.12 | web | Web | Alex | 17.55
2026.12 | app | App | Alex | 15.3562
2026.12 | api | API | Bea | 5.4844
2026.12 | new | New |  | 5.4844
2026.13 | web | Web | Alex | 17.76
2026.13 | app | App | Alex | 15.54
2026.13 | api | API | Bea | 5.55
2026.13 | new | New |  | 5.55
2026.14 | web | Web | Alex | 18
2026.14 | app | App | Alex | 15.75
2026.14 | api | API | Bea | 5.625
2026.14 | new | New |  | 5.625
2026.15 | web | Web | Alex | 18
2026.15 | app | App | Alex | 15.75
2026.15 | api | API | Bea | 5.625
2026.15 | new | New |  | 5.625
2026.16 | web | Web | Alex | 18
2026.16 | app | App | Alex | 15.75
2026.16 | api | API | Bea | 5.625
2026.16 | new | New |  | 5.625

## Prognoses
Sprint | Time | Comment | Commitment (PT) | Expected not finished (PT) | Additionally done (PT) | Expected done | Target sprint | Forecast PLAN | Pre-planning per product (ID=value; …)

## Trend
Sprint | norm. velocity | Ø norm. velocity | norm. velocity trend | Forecast PLAN | Velocity | Commitment
2026.1 | 30 | #N/A | #N/A | 32 | 30 | 32
2026.2 | 30.9091 | #N/A | #N/A | 35 | 34 | 35
2026.3 | 29.4737 | #N/A | #N/A | 33 | 28 | 33
2026.4 | 34.2857 | #N/A | #N/A | 36 | 36 | 36
2026.5 | 33 | 31.5337 | #N/A | 34 | 33 | 34
2026.6 | 30.2439 | 31.5825 | #N/A | 32 | 31 | 32
2026.7 | #N/A | #N/A | 31.5825 | 53 | #N/A | #N/A
2026.8 | #N/A | #N/A | 31.5825 | 60 | #N/A | #N/A
2026.9 | #N/A | #N/A | 31.5825 | 55.7 | #N/A | #N/A
2026.10 | #N/A | #N/A | 31.5825 | 50.5 | #N/A | #N/A
2026.11 | #N/A | #N/A | 31.5825 | 56.8 | #N/A | #N/A
2026.12 | #N/A | #N/A | 31.5825 | 58.5 | #N/A | #N/A
2026.13 | #N/A | #N/A | 31.5825 | 59.2 | #N/A | #N/A
2026.14 | #N/A | #N/A | 31.5825 | 60 | #N/A | #N/A
2026.15 | #N/A | #N/A | 31.5825 | 60 | #N/A | #N/A
2026.16 | #N/A | #N/A | 31.5825 | 60 | #N/A | #N/A